## Line Of Work
SDL GLOBE - HRMS - TASK ASSIGN+B21859
SL No. | Module | Sub module/Submenu | Pages/Sections | Description | Required Time | Delivary Date | Module Name | Status | Developer Name
1 | My Dashbord | Team Members |  | Display Data Team Members & all Employee Data it will display |  | Completed | My DashBord | Completed
2 |  | My Profile |  | Employee View Display & Edit my Profile details |  | Completed | Menu - Configuration | Completed
[6 empty] | Completed | Company | Completed | Prasanna Babu
| Menu-Config | Menu configuration |  |  |  | Completed | Employee | Completed | Prasanna Babu
1 |  |  | Module | Create has to be Module Name,Module Order Submit & data display |  | Completed | leave | Completed | Prasanna Babu
2 |  |  | Parent Module | ddl display Module List & create parent menu,Parent order Submit,reset |  | Completed | Attendance | Work In process | prasanna Babu
3 |  |  | Child Module | Parent menu Display,child menu name,file path,child menu order module |  | Completed
4 |  |  | Role Menu configuration | Role Name,module ddls display assigend menus unassigend menus |  | Completed | Payroll | Pending
5 |  |  | Upload Logo | Attach document upload and submit |  | Completed | Appraisal | Pending
[6 empty] | Completed | Reimbursement | Pending
| Company |  |  |  |  | Completed | traning | Pending
1 |  | Company | Company | Company has To Be Create,Edit/Update/delete/Data Will Display Insert to be table |  | Completed | Query | Pending
2 |  | Work Location | Work Location | Work Location has To Be Create,Edit/Update/delete/Data Will Display Insert to be table |  | Completed | HR Letter | Pending
3 |  | Department Type | Department Type | Department type has To Be Create,Edit/Update/delete/Data Will Display Insert to be table |  | Completed | Exit | Pending
4 |  | Department | Department | Department has To Be Create,Edit/Update/delete/Data Will Display Insert to be table |  | Completed | recruitment | Pending
5 |  | Desgination | Desgination | Desgination has To Be Create,Edit/Update/delete/Data Will Display Insert to be table |  | Completed | onboarding | Pending
6 |  | Employee Type | Employee Type | Employee Type has To Be Create,Edit/Update/delete/Data Will Display Insert to be table |  | Completed | Information Center | Pending
7 |  | Employee Sub Type | Employee Sub Type | Employee Sub Type has To Be Create,Edit/Update/delete/Data Will Display Insert to be table |  | Completed
8 |  | Employee status | Employee status | Employee Status has To Be Create,Edit/Update/delete/Data Will Display Insert to be table |  | Completed
9 |  | Role | Role | Role has To Be Create,Edit/Update/delete/Data Will Display Insert to be table |  | Completed
10 |  | Grade | Grade | Grade has To Be Create,Edit/Update/delete/Data Will Display Insert to be table |  | Completed
11 |  | Currency Code | Currency Code | Currency Code has To Be Create,Edit/Update/delete/Data Will Display Insert to be table |  | Completed
12 |  | State | State | State has To Be Create,Edit/Update/delete/Data Will Display Insert to be table |  | Completed
13 |  | Bank | Bank | bank has To Be Create,Edit/Update/delete/Data Will Display Insert to be table |  | Completed
14 |  | Country | Country | Country has To Be Create,Edit/Update/delete/Data Will Display Insert to be table |  | Completed
15 |  | State | State | State has To Be Create,Edit/Update/delete/Data Will Display Insert to be table |  | Completed
16 |  | City | City | City has To Be Create,Edit/Update/delete/Data Will Display Insert to be table |  | Completed
17 |  | Parent Query Type | Parent Query Type | Parent Query Type has To Be Create,Edit/Update/delete/Data Will Display Insert to be table |  | Completed
18 |  | Query Type | Query Type | Query Type has To Be Create,Edit/Update/delete/Data Will Display Insert to be table |  | Completed
1 | Information Center | Information Center | Vision | Type ddl Display Heading ,description Has To Be Create and Submit |  | Need to assign
2 |  |  | Service Information | Service Information ddl Display Heading ,description,Upload Has To Be Create and Submit |  | Need to assign
3 |  |  | Job Openings | Job Openings ddl Display Heading ,description,Upload Has To Be Create and Submit |  | Need to assign
4 |  |  | Policy dockit | Policy Dockit ddl Display Heading ,description,Upload Has To Be Create and Submit |  | Need to assign
5 |  |  | organisation chart | Organisation chart ddl Display Heading ,description,Upload Has To Be Create and Submit |  | Need to assign
6 |  |  | Buzz | Type,status,priorty,heading,description,upload document has to be create |  | Need to assign
7 |  |  | Event master | Event master Type,status,priorty,heading,description,upload document has to be create |  | Need to assign
8 |  |  | News details | Type,subject,description,upload news details Has to be create |  | Need to assign
9 |  |  | Press Release | Heading ,Description Has to be Create |  | Need to assign
10 |  |  | Announcement Center | Type,status,priorty,heading,description,description has to be create |  | Need to assign
11 |  |  | Achievement master | Type,heading,Description Has to be create |  | Need to assign
12 |  |  | Training Document | Type,subject,description,upload news details Has to be create |  | Need to assign
13 | [5 empty] | Need to assign
14 |  | Information Center ESS | Service Information | Service Information View Data Will Display |  | Need to assign
15 |  |  | Job Openings | Job Openings View Data Will Display |  | Need to assign
16 |  |  | Policy dockit | Policy Dockit View Data Will Display |  | Need to assign
17 |  |  | organisation chart | organisation chart View Data Will Display |  | Need to assign
18 |  |  | Buzz | Buzz View Data Will Display |  | Need to assign
19 |  |  | Event master | Event master View Data Will Display |  | Need to assign
20 |  |  | News details | News details View Data Will Display |  | Need to assign
21 |  |  | Press Release | Press Release View Data Will Display |  | Need to assign
22 |  |  | Announcement Center | Announcement Center View Data Will Display |  | Need to assign
23 |  |  | Achievement master | Achievement master View Data Will Display |  | Need to assign
Need to assign
1 | Recruitment | Recruitement Masters | Create Request Type | Request Type,Description has to be Create |  | Need to assign
2 |  |  | Create vacancy Type | vacancy Type,Description has to be Create |  | Need to assign
3 |  |  | Create Consultancy | Create Consutancy Type,Description has to be Create |  | Need to assign
4 |  |  | Create Skill | Skill Name description Has to Be create |  | Need to assign
5 |  |  | Create funcation | Create funcation area ,Description |  | Need to assign
6 |  |  | Create Qulification | Qulification,description has To be create |  | Need to assign
7 |  |  | Create Ineriew type | Create Interview type has to Be create |  | Need to assign
8 |  |  | Create Interview Pannel | Create Interview Pannel has to Be create |  | Need to assign
9 |  |  | Create CTC Range | Create CTC Range has to Be create |  | Need to assign
10 | [5 empty] | Need to assign
11 |  | Create RRF | CTC Range | Create CTC Range has to Be create |  | Need to assign
12 |  |  | RRF | Pending,approved,Rejected Forms status will Be check |  | Need to assign
13 |  |  | Approve RRF as BH | View data it will Display |  | Need to assign
14 | [5 empty] | Need to assign
15 |  | HR Activities- Recruitment | intiate Recruitement | View data it will Display |  | Need to assign
16 |  |  | consultancies and Employee referrals | consultancies and Employee referrals ha to Be Create |  | Need to assign
17 |  |  | Condidate Registration Form | Condidate Registration Form Has To Be Create |  | Need to assign
18 |  |  | Search Resume | Search Resume has to Be Search Document |  | Need to assign
19 |  |  | Assin Interview Pannel | Assin Interview Pannel has to Be create |  | Need to assign
20 |  |  | Round one Condidate | Select RRF Code display 1st Round,2nd,3nd Ddl Will Display |  | Need to assign
21 |  |  | Round two Condidate | Select RRF Code display 3nd Ddl Will Display |  | Need to assign
22 |  |  | Round three Condidate | Select RRF Code display 3nd Ddl Will Display |  | Need to assign
23 |  |  | Final Confirmed and rejected Candidates | Confirmed,rejected,declined,hold candidate data will display |  | Need to assign
24 |  |  | close vancancy | Vancancy status View It is Display |  | Need to assign
25 |  |  | PUT RRF on Hold | View On hold data will display |  | Need to assign
26 |  |  | Recruitment Report | Generate The Recruitment data |  | Need to assign
27 |  |  | Recruitment Status | Display recruitment Status Display |  | Need to assign
28 |  |  | RRF Change | Edit Update delete Data Will Display |  | Need to assign
Need to assign
Need to assign
1 | On Boarding | Hr WorkFlows | Generate All Forms | Generate All Forms has To be Create and Print Will working check |  | Need to assign
2 |  |  | validate new Emp Details | validate new Emp Details data will display |  | Need to assign
3 |  |  | create canditate login details | Teampaporary Login details has to be create |  | Need to assign
1 | Employee | Hr workflows | Upload Document | Upload Document has To be Create |  | Completed
2 |  |  | Create Employee | Create Employee Details has to Be Create |  | Completed
3 |  |  | Edit Empployee Details | Employee Details Will Update And delete modify data insert to the table |  | Completed
4 |  |  | Employee Directory | Employee Directoty Data Will View display |  | Completed
5 |  |  | Resigned Employee Directory | Resigened Employee Directoty Data Will View display |  | Completed
6 |  |  | Approver As HR | Employee data View Display hr will Approved In employee details |  | Completed
7 |  |  | View status As HR | View status As HR Employee data View Display hr will Approved In employee details |  | Completed
8 |  |  | Update Employee Details | Update Employee Details In Insert To the table data |  | Completed
9 |  |  | View Employee transfor/ Promotion | Ddl display Employee Transfor/promotion |  | Completed
10 | [5 empty] | Completed
11 |  | User Workflows | My Profile | Create My Profile page |  | Completed
12 |  |  | Edit My Profile | Edit My Profile page |  | Completed
13 |  |  | Edit My Profile - status Update | Edit My Profile page /status Update view display staus |  | Completed
14 | [5 empty] | Completed
15 |  | EDB Report | EDB Report | Generate EDB Report
1 | Leave |  | Leave policy | leave registration has to be createview/Edit/Update/delete Modify data insert to table. |  | Completed
2 |  |  | Leave Master | leave Master has to be create view/Edit/Update/delete Modify data insert to table |  | Completed
3 |  |  | Leave Rule | leave rule has to be create view Eidt/Update/Delete Modify data Insert to table leave rule Adjustment create |  | Completed
4 |  |  | Employee Leave Profile | 1)view/edit Leave profile Modify data insert to table. 2)Upload leave Balance document. 3)create Employee Profile |  | Completed
5 |  |  | HR Leave Activites | leave apply & Update By Hr |  | Completed
6 |  |  |  | Leave Encashment Form create to data |  | Completed
7 |  |  |  | process leave Montly has to be create |  | Completed
8 |  |  |  | leave period has to be create |  | Completed
9 |  |  |  | year end leave process drop down List Display. |  | Completed
10 |  |  |  | freeze leave to be display drop down list |  | Completed
11 |  |  |  | upload year ending balance balance document file upload & download excel sheet |  | Completed
Completed
12 |  |  | Leave Reports | Employee Leave Balance ddl form Display Employee balance sheet display |  | Completed
13 |  |  |  | Leave Register to be create |  | Completed
14 |  |  |  | leave details Report Form date To end Date report generate |  | Completed
15 |  |  |  | leave employee Report generate |  | Completed
16 |  |  |  | My reportees yearly leave report |  | Completed
17 |  |  |  | year ending report |  | Completed
18 | [5 empty] | Completed
Completed
19 |  |  | Leave Application | Apply leave has to create |  | Completed
20 |  |  |  | user ending report display |  | Completed
Completed
21 |  |  | Leave status | pending leave |  | Completed
22 |  |  |  | approved leave |  | Completed
23 |  |  |  | cancelled leave |  | Completed
24 |  |  |  | Rejected leave
26 |  |  | Approve Leaves | Approve leave as Manager |  | Completed
27 |  |  |  | All leave Approval Status |  | Completed
Completed
| Attendance | Attendance Master |  |  |  | Completed
1 |  |  | Create Shift Master | attendance Shift has to be createview/Edit/Update/delete Modify data insert to table. | 2024-05-13 | Completed
2 |  |  | Create attendance Rule | attendance Rule has to be createview/Edit/Update/delete Modify data insert to table. |  | Completed
3 |  |  | Create Empcode IP and machine Code Mapping | Create machine Code IP and machine code mapping |  | Completed
4 |  |  | Upload Empcode IP and Machine Code Mapping | Upload machine Code document IP and machine code mapping |  | Need to do (PrasannaBabu)
5 |  |  | Repoart Empcode IP And Machine code mapping | Report machine Code IP and machine code mapping |  | Need to do (PrasannaBabu)
|  |  | Downloand attendance log | Branch drop list Display |  | Need to do (PrasannaBabu)
6 |  |  | Shift mMapping | branch Drop List and upload Chose document |  | Need to do (PrasannaBabu)
7 |  |  | Create holiday Master | Create Holiday Master has to be createview/Edit/Update/delete Modify data insert to table. |  | Need to do (PrasannaBabu)
8 |  |  | weekend Drop List | work Location And week Off ddl display |  | Need to do (PrasannaBabu)
9 |  |  | Date type mapping | date type ddl display from date & end date display |  | Need to do (PrasannaBabu)
10 |  |  | HR Work Flows |  |  | Need to do (PrasannaBabu)
11 |  |  | Procces Attendance | Branch ddl Display and From Date and End Date insert to tabel |  | Need to do (PrasannaBabu)
12 |  |  | over write Attendance | from date and end date,employee Code Display fetch attendance |  | Need to do (PrasannaBabu)
13 |  |  | attendance manual Entry | Employee code,date in Date,out date insert Data |  | Need to do (PrasannaBabu)
14 |  |  | camp Off apply and update by hr | camp off has to be data insert to table. |  | Need to do (PrasannaBabu)
15 |  |  | OD Apply and update by HR | OD has to be data insert to table. |  | Need to do (PrasannaBabu)
16 |  |  | Freeze Attendance | year DDL display and insert |  | Need to do (PrasannaBabu)
Need to do (PrasannaBabu)
17 |  | User Work Flow | User Work Flow | Apply Holiday work |  | Need to do (PrasannaBabu)
18 |  |  |  | Apply OD |  | Need to do (PrasannaBabu)
19 |  |  |  | Apply Camp Off |  | Need to do (PrasannaBabu)
20 |  |  |  | My holiday work status |  | Need to do (PrasannaBabu)
21 |  |  |  | My camp of status |  | Need to do (PrasannaBabu)
22 |  |  |  | my OD status |  | Need to do (PrasannaBabu)
23 | [5 empty] | Need to do (PrasannaBabu)
Need to do (PrasannaBabu)
|  | Approver workflow |  |  |  | Need to do (PrasannaBabu)
1 |  |  | Approver workflow/rejected holiday work | approver/rejected holiday work check status |  | Need to do (PrasannaBabu)
2 |  |  | approver/rejected camp off | approver/rejected camp off check status |  | Need to do (PrasannaBabu)
3 |  |  | approver/rejected OD | approver/rejected OD check status |  | Need to do (PrasannaBabu)
4 |  |  | holiday work status | camp of check view status |  | Need to do (PrasannaBabu)
5 |  |  | camp Off approvel | camp off check status |  | Need to do (PrasannaBabu)
6 |  |  | OD Approvel Status | OD check status |  | Need to do (PrasannaBabu)
7 |  | reports |  |  |  | Need to do (PrasannaBabu)
8 |  |  | montly attendance report | monthly attendance ddl Display and From Date and End Date insert to tabel |  | Need to do (PrasannaBabu)
9 |  |  | date wise attendance report | date attendance ddl Display and From Date and End Date insert to tabel |  | Need to do (PrasannaBabu)
10 |  |  | holiday register report | Holiday register ddl Display and From Date and End Date insert to tabel |  | Need to do (PrasannaBabu)
11 |  |  | campoff regisrer report | champ register report ddl Display and From Date and End Date insert to tabel |  | Need to do (PrasannaBabu)
12 |  |  | campoff details report | champ of report ddl Display and From Date and End Date insert to tabel |  | Need to do (PrasannaBabu)
| PAYROLL |  | PayRoll master
|  |  | Add/vIew payhead | payRoll has to be createview/Edit/Update/delete Modify data insert to table.
|  |  | Add PF/ ESI | payRoll has to be createview/Edit/Update/delete Modify data insert to table.
|  |  | Tax slab | payRoll has to be createview/Edit/Update/delete Modify data insert to table.
1 | Appraisal | E-Evaluation Master
2 |  |  | E-Evaluation cycle | Set e-evaluation cycle |  | Need to assign
3 |  |  | select eligbile employee | Set e-evaluation cycle |  | Need to assign
4 | [5 empty] | Need to assign
5 |  |  | HR WokFlow |  |  | Need to assign
6 |  |  | initiate hike | check data into status |  | Need to assign
7 |  |  | initiate promation | promotion intiate data entry |  | Need to assign
8 |  |  | all employee E-evaluation | ddl display to insert data table |  | Need to assign
9 |  |  | all hike status | recommendation on hike |  | Need to assign
10 |  |  | all promotion status | recommendation on promotion |  | Need to assign
11 | [5 empty] | Need to assign
12 |  |  | user work flow |  |  | Need to assign
13 |  |  | my self rating | ddl create and emprating work flow create data |  | Need to assign
14 |  |  | my evaluation status | view display end modify |  | Need to assign
15 | [5 empty] | Need to assign
16 |  | Approver workflow
17 |  |  | set goals as line manager | create has to create goals |  | Need to assign
18 |  |  | view goals as line manager | view/edit/delete display data and data modify |  | Need to assign
19 |  |  | review rating as business head | review rating & comments, employee list diplay |  | Need to assign
20 |  |  | approver hike to vitrual head | recommendation on hike |  | Need to assign
21 |  |  | approver hike to business head | recommendation on hike check all & uncheck all |  | Need to assign
22 |  |  | line manager e-evaluation | check all & uncheck all proparly data working |  | Need to assign
23 |  |  | businnes head e-evaluation | check all & uncheck all |  | Need to assign
|  | Reports |  |  |  | Need to assign
24 |  |  | E-evaluation report | appraisal status data display |  | Need to assign
25 |  |  | E-evaluation History | all appraisal cycle status diplay view part |  | Need to assign
26 |  |  | Consolidated average rating | appraisal year ddl display |  | Need to assign
26 |  |  | for all employee | quarter ddl display |  | Need to assign
| Reimbursement | Reimbursement Masters |  |  |  | Need to assign
1 |  |  | Create head | create head Shift has to be create |  | Need to assign
2 |  |  | User Workflows | create reimbursement has to be create |  | Need to assign
3 |  |  | My reibursement status | ddl display to insert data table |  | Need to assign
4 |  |  | Approver reibursment as manager | from date and to date check status |  | Need to assign
5 |  |  | Approver reibursment as admin | from date and to date check status |  | Need to assign
6 |  |  | Approver reibursment as business head | from date and to date check status |  | Need to assign
7 |  |  | Approver reibursment as finance spoc | from date and to date check status |  | Need to assign
8 |  |  | Approver reibursment as status | from date and to date search status |  | Need to assign
|  | Reports |  |  |  | Need to assign
10 |  |  | Reimbursement Masters | select data search report display |  | Need to assign
Need to assign
| Training |  |  |  |  | Need to assign
|  | Training Master |  |  |  | Need to assign
1 |  |  | Training Type | training type has to be create |  | Need to assign
|  | User Workflow |  |  |  | Need to assign
2 |  |  | My training Request | view report display |  | Need to assign
3 |  |  | participant feedback Form | participant feedback Form to View Display |  | Need to assign
4 |  |  | Training Form | training Form has to be create |  | Need to assign
5 |  |  | view/edit training schedule | training schedule display data |  | Need to assign
Need to assign
|  | Approver Workflow |  |  |  | Need to assign
6 |  |  | add participants by LM | training schedule view display |  | Need to assign
7 |  |  | view need participants | need participants view display |  | Need to assign
8 |  |  | view participants | need participants view display |  | Need to assign
9 |  |  | Mark Attendance | mark attendance view display |  | Need to assign
10 |  |  | effectiveness feedback form | effectiveness feedback view display |  | Need to assign
11 |  |  | view effectiveness feedback form by LM | view effectiveness feedback view display |  | Need to assign
12 |  |  | view effectiveness feedback form by trainer |  |  | Need to assign
Need to assign
14 |  |  | Reports |  |  | Need to assign
15 |  |  | attendance report | training report Display |  | Need to assign
16 |  |  | view Feedback Form | view Feedback Form Display |  | Need to assign
17 |  |  | team Members training Report | team memners training report view display |  | Need to assign
Need to assign
| Query | User Workflows |  |  |  | Need to assign
1 |  |  | Raise Query | query Form has to be Create |  | Need to assign
2 |  |  | my query Status | view display data my query status |  | Need to assign
Need to assign
|  | Approver Work Flow |  |  |  | Need to assign
3 |  |  | All query status | search the data display |  | Need to assign
Need to assign
|  | Reports |  |  |  | Need to assign
4 |  |  | Data wise Report | query report display form date to end date create data |  | Need to assign
5 |  |  | Department wise Report | all data search data will display |  | Need to assign
Need to assign
| HR Letters | HR Letters |  |  |  | Need to assign
1 |  |  | Generate Letters | create letters and send to mail data store in table |  | Need to assign
2 |  |  | Create Appointment letter | create Appointment letters and send to mail data store in table |  | Need to assign
3 |  |  | Generate confirmation letter | create confirmation letters and send to mail data store in table |  | Need to assign
4 |  |  | Generate Employement & Address Prof letter | create employeement letters and send to mail data store in table |  | Need to assign
5 |  |  | Generate desgination Letter | create desgination letters and send to mail data store in table |  | Need to assign
6 |  |  | Generate Increment Letter | create Increment letters and send to mail data store in table |  | Need to assign
7 |  |  | Generate resignation acceptance letter | create resignation letters and send to mail data store in table |  | Need to assign
8 |  |  | Generate relieving letters | create reliveing letters and send to mail data store in table |  | Need to assign
9 |  |  | Generate Experience letter | create Experience letters and send to mail data store in table |  | Need to assign
10 |  |  | Generate trainee Letter | create trainee letters and send to mail data store in table |  | Need to assign
Need to assign
| EXIT | HR WorkFlows |  |  |  | Need to assign
1 |  |  | All resgination request Status | dll list its will display |  | Need to assign
2 |  |  | Resgination Requests | records diplay in view part |  | Need to assign
3 |  |  | deactivate Account | deactivate employee account |  | Need to assign
|  | User WorkFlows |  |  |  | Need to assign
4 |  |  | My Resgination Request | Approver code aprrove level will check propalry |  | Need to assign
5 |  |  | My Resgination Request Status | approved,pending,rejected check status |  | Need to assign
6 |  |  | Exit Interview Questionnaire | view data its will diplay |  | Need to assign
|  | Approver Workflows |  |  |  | Need to assign
7 |  |  | Resgination Requests | grid data will display records check |  | Need to assign
8 |  |  | Approver resgination requests | approved rejected ddl status will check the data |  | Need to assign
|  | Reports |  |  |  | Need to assign
9 |  |  | exit report | report data will display in exit export page |  | Need to assign
10 |  |  | resgination History | report data will display in exit resgination page |  | Need to assign

## Daily Work Update
SDL GLOBE DAILY TEAM WORK UPDATES
Name | Date | Task | Review Status
Prasanna Babu
| 14/05/2024 | Create Empcode IP Address Under Attendance Module Machine Code Mapping Under attendance Module.. | Discuss with Sir
| 15/05/2024 | 1) Machine Code Mapping Under attendance Module.. | Discuss with Sir
| 16/05/2024 | - Upload Empcode ID Under & Machine Code Mapping attendance Module.. | Discuss with Sir
| 20/05/2024 | 1) Create Empcode IP Address Under Attendance Module 2) Machine Code Mapping Under attendance Module.. 3)Upload Empcode ID Under & Machine Code Mapping attendance Module.. | Discuss with Sir
| 21/05/2024 | working on yesterday pending task upload employee information prop under Empcode ID & Machine Code Mapping page which comes under attendance module. | Discuss with Sir
Rajesh | 14/05/2024 | Working on assign Parent Menu & Child Menu Explain Under Menu Configuration Implementation Try & Catch blocks. | Task Completed
| 15/05/2024 | Create Sample Page Under leave Module.... & Implementation Try & Catch blocks | Task Completed
| 16/05/2024 | Creating one Job type field in Employee Module and Storing that data in Database | Task Pending
| 17/05/2024 | Creating one Job type field in Employee Module and Storing that data in Database | Task Completed
| 18/05/2024 | Adding one Column in Experience Gridview in Employee Module | Task Completed
| 20/05/2024 | Understanding the Workflow document of Attendance Module | Task Completed
| 21/05/2024 | working on Employee Promotion/ transfer ddl display under employee module
Manasa | 14/05/2024 |  | Task Completed
| 15/05/2024 | Create Sample Page Under Employee Module.... &Implementation Try & Catch blocks | Task Completed
| 16/05/2024 | Creating a Job type field in Employee Module And Storing the data in Database.. | Task Pending
| 17/05/2024 | Creating a Job type field in Employee Module And Storing the data in Database.. | Task Completed
| 18/05/2024 | Creating a Column In Training Gridview under Employee Module. | Task Completed
| 20/05/2024 | To Understanding the Leave Module Workflow of Document | Task Completed
| 21/05/2024 | Leave Apply to HR activities Under Leave Module
Note on A3: Author: